## Delivery_Plan
Client | Delivery Date | Support Representitive | Technical Reporesentitive | New-Optima Delivery | Homers Delivery | Migrate Old Homers | Cleaning Tool Delivery | Delivery Status | Visit Report#
ElAmin | 2015-07-01 | Mohamed Ghazaly | Eman Mohamed | x | x | x | x

## Homers Testing Plan
Phase | Task | Required Effort /Hr
Installation | Install HO | 1
Installation | Install Web Service | 1
Installation | Install Branch | 1
Comsys Structure | Create | 8
Comsys Structure | Update | 8
Comsys Structure | Delete | 8
Security Module | Create | 4
Security Module | Update | 2
Security Module | Delete | 2
General Codes | Getting New Codes from HO | 16
General Codes | Getting Updated Codes from HO | 16
General Codes | Delete deleted Codes from HO | 16
Testing Transactions | Sending Create new transactions in Branch to HO | 16
Testing Transactions | Sending Updated transactions in Branch to HO | 16
Testing Transactions | deleting deleted transactions in Branch from HO | 16
Totals Effort Per Hours |  | 131
Totals Effort Per Days |  | 18.7143
Expected Start Date |  | 2015-05-24
Expected End Date |  | 2015-06-19 04:48
Formulas:
Required Effort /Hr = [Required Effort /Hr, row above]+C21*7/5

## ClientsProfile
Client Name | No. Branches | Installed Modules | Homers | Homers Branches
Sino Stores
Tagoury | 3
3Brothers
GANA
Kouadis
Joly
New Alfa
Alarab
ElAmin

## TechnicalRepresentitives
Name | Role | Tel | Email Address
Eman Mohamed | Technical TL

## Implementation Representitives
Name | Role | Tel | Email Address
Mohamed Ghazaly | Lead Consultant
Ahmed Abdel Azim | Service Leader